## 1. Product Overview
Item | Description
Product Name | AI Contract & Financial Intelligence Platform
Product Vision/ Purpose | To develop an AI-powered platform that simplifies complex contracts, detects risks, and analyzes financial impact to help users make informed decisions before signing agreements.
Business Goals / Key Success factors | Enable users to understand contracts quickly and easily, achieve high accuracy in risk detection and financial analysis, reduce dependency on legal experts, and provide fast, reliable, and user-friendly contract insights.
Primary Stakeholders | startups, small businesses.

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email and OTP so that I can access my account securely. | Registration screen | Must Have | 8 | To Do | Backend Team | Test signup & OTP flow | QA team
|  |  |  | OTP generation |  |  |  |  | Validate OTP creation
|  |  |  | sending OTP |  |  |  |  | Test OTP delivery
|  |  |  | login screen |  |  |  | Frontend dev Team | UI login testing
|  |  |  | error handling |  |  |  |  | Test invalid login
| User Login & Session | US2 | As a user, I want to log in to my account so that I can access my dashboard. | Login AP | Must Have | 8 | To Do | Backend Dev Team | Test login API | QA Team
Session handling
| User Logout | US3 | As a user, I want to log out securely so that my account remains safe. | Logout API | Should Have | 5 | To Do | Backend Dev team | Test logut | QA team
Session Terminating
E2 | Dashboard | US4 | As a user, I want to upload a contract so that I can analyze it. | File upload (PDF/DOC) | Must Have | 13 | In Progress | Backend Dev team | Test file upload | QA Team
| Contract Analysis |  |  | File validation
| Insights – Summary | US5 | As a user, I want to view contract summary and key clauses so that I can understand the agreement easily. | Text extraction | Must Have | 8 | In Progress | AI/Backend Team | Validate extracted text | QA Team
|  |  |  | Summary generation |  |  |  | AI Team
|  |  |  | Clause extraction |  |  |  | AI Team
| Risk Detection | US6 | As a user, I want risk detection so that I can identify risky clauses. | Risk detection engine | Must Have | 13 | To Do | AI Team | Test risk scoring | QA Team
|  |  |  | Risk scoring logic |  |  |  | Backend Dev team Names
| Financial Analysis | US7 | As a user, I want to see financial impact so that I can understand costs and penalties. | Financial calculation module | Must Have | 13 | To Do | Backend Dev team Names | Validate Calculations | QA Team
Simulation logic
| Chatbot Support | US8 | As a user, I want a chatbot so that I can ask questions about the contract. | Chatbot integration | Should Have | 8 | In Progress | AI Team | Test chatbot responses | QA Team
Prompt handling
| Multilingual Support | US9 | As a user, I want multilingual support so that I can understand contracts in my language. | Translation API | Could Have | 5 | To Do | Backend Dev team Names | Test translation | QA Team
|  |  |  | Language selection UI |  |  |  | Frontend dev team

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-03-15 | Authentication, Contract Upload | None | On Track
v0.2 | 2026-03-22 | Text Extraction, Contract Summary | OCR/NLP setup | Planned
v0.3 | 2026-03-29 | Clause Extraction, Risk Detection | AI/NLP model | Planned
v0.4 | 2026-03-06 | Risk Scoring, Risk Display | Data processing logic | Planned
v0.5 | 2026-04-13 | Financial Impact Simulator | Financial data extraction | Planned
v0.6 | 2026-04-20 | Chatbot Integration | AI model API | Planned
v0.7 | 2026-04-26 | Dashboard UI, Full System Integration | All modules combined | Yet to Plan
v1.0 | 2026-05-03 | Multilingual Support, Final Improvements | Translation API | Yet to Plan

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead